## Status Legend
Code | Meaning | Use
CERTIFIED | Loaded, normalized, validated, and formal certification passed | Ready for downstream analysis subject to stated methodological limits
VALIDATED | Loaded and validation checks passed | Strong dataset; certification/evidence package may still be pending
LOADED | In database but final validation/certification not yet established | Do not treat as final analytical input
ACQUIRED | Raw source data preserved locally | ETL/normalization still required
PARTIAL | Only part of the required population/year is available | Not complete for annual balance calculation
DEVELOPED | Method/reporting implementation exists; exact year-by-year release coverage should be verified | Useful infrastructure, but matrix not yet closed
NOT STARTED | Required data not yet acquired/implemented | Coverage gap
N/A | Not applicable to this control row | —

## FY2015-FY2024 Matrix
Dataset / Category | FY2015 | FY2016 | FY2017 | FY2018 | FY2019 | FY2020 | FY2021 | FY2022 | FY2023 | FY2024 | Role / Current Note
IRS SOI county income/tax data | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | NOT STARTED | NOT STARTED | County geographic basis for federal-receipt allocation; 360 rows/year validated for 2015-2022.
IRS Data Book Table 5 gross collections | VALIDATED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | LOADED | NOT STARTED | LOADED | NOT STARTED | LOADED | State/control receipt series. FY2015 release validation passed; later loaded years require final series reconciliation/status verification.
SSA OASDI county benefits | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | VALIDATED | 39 counties × 9 benefit types; county dataset validated across 2015-2024.
Medicare | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | State reporting implementation exists; Original Medicare represented; Medicare Advantage not fully represented. Exact annual release coverage to verify.
Medicaid | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | Washington state expenditure reporting implemented from CMS MBES controls; county allocation remains to be developed/validated.
CHIP | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | Washington state expenditure reporting implemented from CMS-21 controls; county allocation remains to be developed/validated.
USAspending procurement/contracts | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | PARTIAL | NOT STARTED | NOT STARTED | NOT STARTED | CERTIFIED | FY2024 certified: 120,813 transactions / 111,083 awards. FY2020 native target=110,244; 49,900 paged diagnostic rows preserved while USAspending service is degraded.
USAspending grants/assistance | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ACQUIRED | ACQUIRED | ACQUIRED | ACQUIRED | ACQUIRED | Native raw assistance data acquired for FY2020-FY2024; FY2025 also acquired outside principal matrix. Normalization/certification remains.
Veterans benefits | LOADED | LOADED | LOADED | LOADED | LOADED | LOADED | LOADED | LOADED | LOADED | LOADED | VA GDX county-level expenditure workbooks acquired and fingerprinted for FY2015–FY2024. FY2015–FY2023 use LEGACY_STATE_SHEETS. FY2024 uses REVISED_DIRECT_INDIRECT and is an explicit methodology break. Overlap with USAspending-derived VA expenditures must be reconciled before GDX totals are treated as additive to the final fiscal-balance ledger.
Federal civilian wages | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Major Rockefeller-style expenditure category still required.
Active-duty military wages | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Required compensation category; geographic attribution methodology needed.
Federal civilian retirement | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Required direct-payment/retirement category.
Military retirement | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Required direct-payment/retirement category.
SSI | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Required direct-payment category distinct from OASDI.
Nutrition assistance | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Required remaining direct-payment category/inventory item.
Housing assistance | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Required remaining direct-payment category/inventory item.
Education / student assistance | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Required remaining direct-payment category/inventory item.
Refundable tax credits / direct payments | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Requires explicit scope and reconciliation to avoid overlap with receipts or assistance.
Other federal direct payments | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | Residual inventory/reconciliation category; define before final completeness certification.
Census PEP population controls | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | DEVELOPED | Supporting denominator/control series; final annual state/county series and certification still to close.
Rockefeller state BOP benchmark | PARTIAL | PARTIAL | PARTIAL | PARTIAL | PARTIAL | PARTIAL | PARTIAL | PARTIAL | PARTIAL | PARTIAL | External statewide benchmark/reconciliation layer; master evidence series still being completed.

## Category Register
Domain | Primary source / control | Geography target | Current position | Principal remaining work
Federal receipts | IRS SOI county + IRS Data Book Table 5 + Rockefeller benchmark | County with state control | IRS SOI 2015-2022 validated; state receipt controls incomplete | Complete 2023-2024 SOI; complete/reconcile annual state receipt controls; define final county allocation methodology
Social Security / OASDI | SSA county benefit data | County | 2015-2024 county data validated | Reconcile annualized December measure to desired FFY accounting convention; certify analytical output
Medicare | CMS | State → county | Reporting implementation exists | Close Medicare Advantage gap; establish county allocator; verify annual coverage and certify
Medicaid | CMS MBES | State → county | Washington state control implementation exists | Develop defensible county allocator and certify
CHIP | CMS-21 | State → county | Washington state control implementation exists | Develop defensible county allocator and certify
Procurement | USAspending Contracts Prime Transactions | Place of performance → county | FY2024 certified end-to-end | Acquire/certify remaining FY2015-FY2023; resume FY2020 native export after service recovery
Grants / assistance | USAspending Assistance Prime Transactions | Place of performance / recipient / program-specific | FY2020-FY2025 raw acquisition strong | Normalize, validate, certify; acquire FY2015-FY2019; finalize geography rules
COVID / extraordinary spending | USAspending DEF codes + award/transaction evidence | County where feasible | Preserve/tag methodology established | Complete transaction-level classification; publish inclusive and COVID-excluded views
Veterans | VA / federal expenditure controls | County | Not started | Acquire annual county/state benefits and validate
Federal & military compensation | Federal payroll/personnel/expenditure sources | County | Not started | Select authoritative sources and geographic allocation methodology
Federal & military retirement | Federal retirement/payment sources | County | Not started | Select authoritative sources and geographic allocation methodology
Other direct payments | Program-specific federal sources | County | Inventory incomplete | Define exhaustive scope, avoid double counting, acquire and certify
Population controls | Census PEP | County/state | Supporting framework identified | Finalize consistent annual denominator series
External validation | Rockefeller Institute State Balance of Payments | State | Evidence/reconciliation framework in progress | Complete master series and compare independently constructed WA totals

## Executive Status
WCFFBP DATASET COVERAGE & PROJECT STATUS
Status date | August 12, 2026
Primary analytical window | FY2015-FY2024
Ultimate metric | Federal taxes originating from each Washington county minus federal expenditures attributable to that county
Guiding principle | Measure first. Explain later.
Current assessment | Beyond proof-of-concept; core database, geography, provenance and certification architecture are operational. Primary task is now closing the year × category coverage matrix.
Strongest completed expenditure dataset | FY2024 USAspending procurement: CERTIFIED; 120,813 transactions, 111,083 awards, all 39 counties, $15,355,300,329.56 obligations; 37 checks passed, 0 failed, 1 warning.
Strongest completed county direct-payment series | SSA OASDI county data validated for 2015-2024 (39 counties, 9 benefit types).
Receipts status | IRS SOI county data validated for 2015-2022. State receipt controls and 2023-2024 SOI remain incomplete, so final county receipt estimates are not yet ready.
USAspending current issue | FY2020 procurement native population independently counted at 110,244 transactions. Native/download services are currently returning failures/HTTP 503; 49,900 paged diagnostic rows are safely preserved but are not being substituted for the preferred native export.
Largest remaining substantive gaps | Historical procurement; pre-2020 assistance; Veterans; federal/military wages and retirement; remaining direct payments; final receipts controls/allocation; Medicare Advantage; county allocation for state-only programs.
COVID treatment | Preserve all observations; identify/tag extraordinary COVID spending; support inclusive and COVID-excluded views where feasible.
Final balance calculation | NOT YET APPROPRIATE until required receipt and expenditure categories have adequate annual coverage and state/county reconciliation.
Evidence note | Status labels reflect evidence currently established in project records. DEVELOPED/PARTIAL is used where implementation exists but exact annual coverage or final certification is not yet closed.